## Gantt
Create a Gantt Chart in this worksheet. Enter title of this project in cell B1. Legend title is in cell I1. Information about how to use this worksheet, including instructions for screen readers and the author of this workbook is in the About worksheet. Continue navigating down column A to hear further instructions. | Customer Churn Prediction and Analysis | [5 empty] | Legend:
Enter Company Name in cell B2. A legend is in cells I2 through AC2. | [6 empty] | On Track |  |  |  |  | Low Risk |  |  |  |  | Med Risk |  |  |  |  | High Risk |  |  |  |  | Unassigned
Enter the name of the Project Lead in cell B3. Enter the Project Start date in cell F3 or allow the sample formula to find the smallest date value from the Gantt Data table. Project Start Date: label is in cell D3. | Project Lead:Sara Subeh |  | Project Start Date: |  | 2025-01-01
A Scrolling Increment is in cell F4. Months for the dates in row 5 are displayed starting in cells I4 through cell BL4. Do not modify these cells. They are auto updated based on the project start date in cell F3. | Project Team:Sara Subeh-HAIDY HESHAM-Abdelrahman-Omar Mohamed |  | Scrolling Increment: |  | 0 |  | January | [34 empty] | February
Cells I5 through BL5 contain the day number of the month for the Month represented in the cell block above each date cell and are auto calculated. Do not modify these cells. Today's date is outlined in Red (hex #AD3815) from today's date in row 5 through the entire date column to the end of the project schedule. | time axis 2025-01-01 to 2025-02-25
A scrollbar is in cells I6 through BL6. The increment for paging through the data is defined as 2 pages at a time and can be configured in the settings for the control bar. To jump forward or backward in the timeline, enter a value of 0 or higher in cell F4. A value of 0 takes you to the beginning of the chart.
This row contains headers for the project schedule that follows below them. Navigate from B7 through BL7 to hear the content. The first letter of each day of the week for the date above that heading, starts in cell I7 and continues through cell BL7. All project timeline charting is auto generated based on the category, start date and number of days entered in the Milestones table. | Milestone Description | Category | Assigned To | Progress | Start | No. Days | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T
Do not delete this row. This row is hidden to preserve a formula that is used to highlight the current day within the project schedule.
Enter Project information starting in cell B9 through cell G9. Sample data is in cells B9 through G33. Enter Milestone Description, select a Category from the drop-down list, assign someone to the item, enter the progress, start date and number of days for the task to start charting. The next instruction is in cell A34. | Milestone 1: Data Collection, Exploration, and Preprocessing |  | HAIDY HESHAM
Title 1:Data Collection
| Task 1:Acquire a churn dataset from sources like Kaggle, UCI Repository, or generate synthetic data | High Risk |  | 100% | 2025-01-01 | 10
| Task 2:Ensure the dataset includes key features such as customer demographics, usage patterns,subscription details, et |  |  | 0%
Title 2:Data Exploration
| Conduct exploratory data analysis (EDA) to understand the dataset’s structure and identify potential relationships between features. |  |  | 0%
| Check for missing values, duplicates, and outliers. Summarize data distributions and basic statistics |  |  | 0%
Title 3:Preprocessing and Feature Engineering
| Task 1:Address missing data through imputation or removal |  |  | 0%
| Task 2:Handle outliers and ensure data consistency |  |  | 0%
| Task 3:Transform features using techniques like scaling, encoding categorical data, and creating interaction features relevant to churn prediction |  |  | 0%
Title 4:Exploratory Data Analysis (EDA)
| Task 1: Create visualizations (heatmaps, pair plots, histograms) to detect patterns, correlations, and outliers. |  |  | 0%
| Task 2:Document key patterns and relationships in the data. |  |  | 0%
Title 5:Deliverables
| Task 1: EDA Report: A document summarizing key insights from data exploration and preprocessing decisions. |  |  | 0%
| Task 2: Interactive Visualizations: An EDA notebook showcasing visualizations that reveal key patterns and relationships. |  |  | 0%
This is an empty row | Task 3: Cleaned Dataset: A dataset that is cleaned and prepared for machine learning |  |  | 0%
| Milestone 2: Advanced Data Analysis and Feature Engineering |  | Sara Subeh
Title 1:Advanced Data Analysis
| Task 1:Conduct statistical tests (e.g., t-tests, ANOVA, chi-squared tests) to explore feature relationships with churn. |  |  | 0%
| Task 2:Use techniques like correlation matrices and recursive feature elimination (RFE) to identify the most relevant features for churn prediction |  |  | 0%
Title 2:Feature Engineering
| Task 1:Create new features such as customer tenure, usage patterns, frequency of interactions, or other indicators of engagement. |  |  | 0%
| Task 2:Apply feature scaling, transformation, or encoding (log scaling, normalization) to improve model performance. |  |  | 0%
Title3:Data Visualization:
| Task 1:Create advanced visualizations (e.g., segmentation of churned vs. non-churned customers) and build dashboards to illustrate churn trends, customer behaviors, and feature importance. |  |  | 0%
Title 4 :Deliverables:
| Task 1: Data Analysis Report: A comprehensive report on statistical analysis and insights derived from advanced feature analysis |  |  | 0%
| Task 2:Enhanced Visualizations: Interactive, insightful visualizations or dashboards that highlight churn- related trends and important features. |  |  | 0%
| Task 3:Feature Engineering Summary: Documentation outlining new features, transformations, and their expected impact on model performance. |  |  | 0%
| Milestone 3: Machine Learning Model Development and Optimization |  | Omar Mohamed
| Milestone 4: MLOps, Deployment, and Monitoring |  | Abdelrahman
Title 1 : MLOps Implementation:
Task 1: Use tools like MLflow, DVC, or Kubeflow for managing model experiments, versions, and deployments.
Task 2:Log metrics, parameters, and artifacts to ensure reproducibility and traceability
Title 2 : Model Deployment:
Task 1:Deploy the final model as a web service or API using frameworks such as Flask or FastAPI.
Task 2: Optionally deploy to cloud platforms (e.g., AWS, Google Cloud, Azure) to ensure scalability.
Task 3: If applicable, build an interactive dashboard or web application using Streamlit or Dash for real-time predictions
| Milestone 5: Final Documentation and Presentation |  | All Team
Title 1 : Final Report
Task 1:Provide a comprehensive summary of the project, including the problem definition, data exploration, model development, and deployment
Task 2:Discuss the business implications of churn prediction and how it can help reduce churn and improve customer retention.
Task 3:Highlight key insights, challenges, and decisions made during the project.
Title 2 :Final Presentation:
Title 3 :Future Improvements
This row marks the end of the Gantt milestone data. DO NOT enter anything in this row. To add more items, insert new rows above this one.
To add more data, Insert new rows ABOVE this one

## About
About This Template
This template provides a simple way to create a Gantt chart to help visualize and track your project. Simply enter your tasks description, select a category of Goal, Milestone, On Track, Low Risk, Med Risk, High Risk, Progress as a percent of task completion, a Start Date and Number of days to complete the task. The Gantt chart fills in and is color coded to help distinguish the various categories. A scroll bar allows you to scroll through the timeline. Insert new tasks by inserting new rows.
Guide for Screen Readers
There are 2 worksheets in this workbook. Gantt Chart About The instructions for each worksheet are in the A column starting in cell A1 of each worksheet. They are written with hidden text. Each step guides you through the information in that row. Each subsequent step continues in cell A2, A3, and so on, unless otherwise explicitly directed. For example, instruction text might say "continue to cell A6" for the next step. This hidden text will not print. To remove these instructions from the worksheet, simply delete column A.
This is the last instruction in this worksheet.